## Sheet1
Budget of Time |  | Date | Start | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-11 | 2016-07-13 | 2016-07-14 | 2016-07-20
Project |  | actual | 60 | 52 | 46 | 40 | 34 | 27 | 21 | 15 | 7.5 | 0
Total Hours | 60 | estimated | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 12 | 6 | 0
Tasks
Javascript Practical Examples | 20
Javascript Practical Tests | 15
Evaluation of Co-operative education project | 23
ECMA6 | 2
Task | Objective | Estimated | Remaining
Javascript Practical Exercises | Setup and Run tests | 8 | 0
| write model answer | 10 | 0
| write hollow answer | 2 | 0
Javascript Practical Tests | Write Model answer | 10 | 0
| Write documentation | 4 | 0
| Write hollow answer | 1 | 0
Evaluation of Co-operative education project | Collate results based on good/recommendations | 10 | 0
| Write documents | 10 | 0
| Proof-read and changing | 5 | 0
ECMA6 | Research - http://es6-features.org | 1 | 0
| Writing ToyBox example | 1 | 0